Ministry of Education, Youth and Sport

Managing Authority of the OP RDI

CALL NO. 7.3 FOR SUBMISSION OF PROJECTS

IN PA 3 OF THE OP RDI

Support for pre-seed activities

| Call identification | Support for pre-seed activities |
| --- | --- |
| Priority axis | 3 – R&D Commercialization and Popularization |
| Area of Support | 3.1 – Commercialization of Results of Research Institutions and Protection of Their Intellectual Property Rights |
| Call number | 7.3 – Support for pre-seed activities |
| System of collecting applications | Round call |
| Date of call announcement | 7 January 2013 |
| Call deadline | 20 March 2013 |
| Receiving project applications under call | February 2013 – 20 March 2013 at the address of the announcer and support provider |
| Planned allocation for the call | CZK 600 million |

Contents:

1	Main stipulations	3

2	Objectives of the call	3

2.1	Main objective of the call	3

2.2	Specific Objectives of the Call	3

2.3	Form of expected results	4

3	Supported activities	6

4	Grant beneficiary	7

4.1	The definition of eligible entities	7

4.2	The main objective of the beneficiary	7

4.3	Additional requirements for the beneficiary	7

4.4	Location of project implementation	8

5	Form and amount of support	8

6	Implementation period and expense eligibility	10

7	Application for support and its submission	10

8	Other provisions	11

9	Address of the announcer and support provider	11

10	Annexes	11

# Main stipulations

The call is announced and the support will be provided by the Managing Authority (MA) of the Operational Programme Research and Development for Innovations – Ministry of Youth, Education and sports (MEYS, www.msmt.cz). Support for pre-seed activities is based on Government Resolution No. 295/2010.

# Objectives of the call

## Main objective of the call

The main objective of the call is to support the preparation of commercialization of promising technologies and inventions with high application potential, which are developed at universities and research institutions.

## Specific Objectives of the Call

Specific objectives of the call focus on the areas necessary for the commercialization of research results. Commercialization of research results is a challenging process, which includes a series of preparatory phases. When compiling the application, the applicants shall take into account the state of their commercialization activities and provide realistic and specific goals, including the form of the expected results to be achieved.

Specific objectives include, in particular:

- Searching for and evaluating the commercial potential of R&D results and their preparation for commercialization. The results of R&D must be 100% owned by the applicant and potential project partners.

- Market survey on the applicability of existing research results 100% owned by the applicant and potential project partners.

- Incorporating results of the survey:

- completion of scientific and technical aspects;

- intellectual property protection and its access enabling conditions;

- preparation of a commercialization plan and a method of commercialization;

- identification and addressing of possible commercial partners.

- Preparation of commercialization by means of (only preparatory works are funded):

- contract-based research work with a commercial entity;

- licensing of research results to a commercial entity;

- the establishment of a start-up or a spin-off company.

- Development of capacities for technology transfer:

- creating mechanisms and structures for the use of revenue from commercial activities for further development of pre-seed activities and research institutions involved in the commercialization, such as pre-seed investment funds and investment committees;

- twinning with foreign as well as advanced local institutions;

- creation, stabilization, support and professionalization of implementation teams for technology transfer and building their practical experience in this area;

- creation, stabilization or development of infrastructure and systems for support of  technology transfers and commercialization;

## Form of expected results

Implementation activities are preceded by the Project preparation key phase.

The project implementation activities will be carried out and evaluated in two key phases:

- Proof of Concept

- Preparation of commercialization – excludes main commercial activities (e.g. contractual cooperation, license sale, operation of the new company, etc.).

Project preparation

The input for the achievement of project outcomes are the existing R&D results being prepared for commercialization (100% owned by the applicant and potential project partners) and preliminary market research, including the market use conditions, stated in the Project Application.

The applicant must have an initial idea of the commercialization direction at the time of submitting the application. The preliminary plan might be changed during the project implementation, including adjustments based on the Proof of Concept phase results.

The preliminary commercialization preparation plan includes, among other things:

- mapping of R&D results suitable for the preparation of commercialization;

- mapping the market potential, particularly the analysis of commercial entities offering similar technologies and competitive products, technologies or services. It serves as a basis for preliminary proposal of the commercialization type. A specific commercial project partner is not expected during the preparation of the project.

- strategy and parameters of the Proof of Concept evaluation;

- preliminary proposal of commercialization method, in particular:

  - contract-based research work;

  - license;

  - the establishment of a start-up or a spin-off company;

- preliminary proposal of intellectual property protection and its access enabling conditions (patent, utility/industrial design, licensing, co-operation agreement regulating the terms of ownership of the results, etc.).

Project implementation activities

The project implementation team for technology transfers supports preparation of commercialization of promising R&D results identified in the application as individual activities (IA). Within the application, the team capacity can be extended and supported to provide (to the applicant and potential partners) evaluation and preparation of commercialization of R&D results that are not explicitly mentioned under individual activities. In this case of the preparation of commercialization of R&D results, which are not identified as IA, the applicant shall indicate the expected number of R&D results:

- analyzed in terms of commercial potential;

- that will enter the Proof of Concept phase;

- that will enter the Preparation for Commercialization phase.

- Proof of Concept – is based on market conditions and market use. It is the preparatory phase for reaching the market potential of research results. During the Proof of Concept activities that include answers to the "how" questions, market survey is updated that includes the "why?" information. Proof of Concept includes completion of technology and preparatory commercialization activities as given by the market research and the state of research results of the applicant and partners. During verification and completion of technology, is neither possible to develop the final product, nor to start the technology research from the scratch.

The Proof of Concept phase output primarily includes:

- Verification of technical feasibility:

    - updated commercialization plan;

    - prototype or functional sample that fulfils the requirements of the subsequent commercialization whose technical completion can continue during the phase of commercialization preparation purely for time reasons;

    - verification of the research results by testing.

- Verification of commercial aspects, including in particular:

    - updated commercialization plan;

    - updated and justified proposal of intellectual property protection plan, including its access enabling conditions (utility/industrial design, licenses, co-operation agreements governing the terms of ownership of the outcomes, patents, etc.) and its preparation; The minimum output is a patent application, if the R&D outcome is patentable, and if the patent application is appropriate;

    - preparatory commercialization activities and their preliminary outputs and proposals in the area of commercialization (but not concluded contracts themselves), such as:

    - contract research work – finding a suitable partner, preparing the conditions under which cooperation will take place, the preparation of the contractual relationship, memorandum of understanding (MoU), letter of intent (LoI);

    - licenses – draft license conditions/payments, draft license agreement, interest declared by an industrial partner (MoU, LoI);

    - founding a start-ups or spin-offs – drafting documents and contracts, drafting the method to transfer intellectual property and other necessary documents.

- Phase “Preparation of commercialization” – selected individual activities from the Proof of Concept phase will be elaborated up to the stage when it is possible to enter a commercial activity of selected type. Commercial activities need not commence right upon finishing the project, but they are expected in the sustainability period. During the Preparation of commercialization phase, similar activities to the Proof of concept phase are performed. The expected outputs are mainly the following completed commercialization preparation activities:

    - final commercialization plan;

    - prepared method of IPR protection and its access enabling conditions  (patent, utility/industrial design, filed patent/design application, license preparation, co-operation agreements regulating the terms of ownership of the outcomes, etc.);

    - completed preparatory commercialization works and their outcomes in selected areas of commercialization such as:

- contract research work – identifying a potentially suitable partner, creating the conditions under which cooperation will take place, (contractual relationship, memorandum of understanding (MoU), letter of intent (LoI), etc.);

- license – elaboration of license conditions, payments, a prepared licensing agreement, interest declared by the industrial partner (MoU, LoI);

- founding a start-up or spin-off  company – necessary documents and agreements, resolving the relationship with the research organization, the way of the IPR transfer, and other necessary documents.

Depending on the type of expected outcomes, the applicant may also register for an optional indicator monitoring the number of filed applied research outcomes according to the Results Information Register (RIR) methodology:

- P – patent;

- Z – pilot plant, proven technology;

- F – results with legal protection – utility model, industrial design;

- G – technically realized results – prototype, functional sample;

- N – certified methods and procedures, including specialized maps with expert content;

- R – software.

# Supported activities

- Founding of teams for commercialization of promising technologies and inventions within each individual activity. Teams may be composed of both specialists in the field of technical implementation (primarily) and in the area of technology transfer.

- Founding, development, or professional stabilization of implementation teams for technology transfer. The team prepares commercialization of individual activities or searches for other suitable R&D results for commercialization and then prepares their commercialization. The team may be composed of both specialists in the field of technology transfer (primarily), intellectual property protection and in the field of technical implementation.

- Consulting, legal and financial services (coaching, training of personnel using foreign expertise, studies, market research, intellectual property protection, patent or industrial design/utility model application, work with potential investors, preparing contracts, ...) necessary to ensure commercialization.

- Twinning with foreign and advanced domestic technology transfer centers, including the fellowship of professionals at the beneficiary site or at another site. Building contacts and networks in order to increase the efficiency of the technology transfer and creation of support for organizations, where building a separate TTO is not effective.

- Activities leading to searching and identification of incoming R&D results, 100% owned by the applicant and potential partners, which are suitable for commercialization, and their preparation for commercialization.

- Activities leading to proof of concept and commercialization, in particular:

- Verification of technical feasibility:

- development of a demonstration model, its components, acquisition of software, necessary licenses and technology transfer database access;

- testing in laboratories, including unique equipment and technology rental.

- Verification of the commercial aspect:

- commercialization plan, detailed market survey, especially the identification and analysis of commercial entities offering similar technologies;

- the intellectual property treatment.

- Preparation of commercialization, particularly:

- research co-operation – searching and identifying of the commercial partner, specification of its share in the expenses and revenues and specification of the cooperation model;

- licensing;

- preparing start-up or spinoff company establishment – only initial expenses for establishment are eligible, while operational costs are not.

- Establishment, stabilization and development of the system and organizational culture that supports commercialization of R&D results and handling of IPR. It also includes implementation of information systems (software) supporting the technology transfer infrastructure. Securing a responsive and efficient process of technology transfer by clearly defined rules and setting up processes for commercialization of R&D results inside research organizations;

- Creation of mechanisms and structures for the use of revenue from commercial activities, such as pre-seed investment funds or investment committees composed of the applicant's staff and external experts, managed by the grant beneficiary.

- Other activities necessary to achieve the objectives of the call, if applicable.

Key activities of the commercialization preparation must be provided by the project team.

# Grant beneficiary

## The definition of eligible entities

- legal persons meeting the definition of a research organization under the Community Framework for State Aid for Research and Development and Innovation 2006/C 323/01 (the Framework).

## The main objective of the beneficiary

- Perform basic research, applied research or experimental development;

or;

- spread results of activities listed under a) through education, publishing or technology transfer.

## Additional requirements for the beneficiary

- All profit from activities listed in Section 4.2 shall be reinvested in these activities;

- Companies (as entities performing commercial activities) that can influence such an entity, e.g. in the capacity of shareholders or members, do not have any preferential access to the research capacities of the entity or the results of the research for the purpose of their commercial activities and paid from the OP RDI funds or other public funds.

- Commercial and non-commercial activities are recorded in separated books, and commercial activities are not financed from non-commercial ones (including the obligation to use profit from non-commercial activities exclusively for them).

A binding way of proving that these conditions have been fulfilled will be stipulated in the OP RDI Handbook for Applicants.

Participation of partners (entities having a share in eligible project expenses) must fulfill conditions stipulated in the OP RDI Handbook for Applicants.

## Location of project implementation

Projects must be implemented in the Czech Republic, but outside the territory of Prague.

The beneficiary as well as the partner must fulfill one of the following conditions related to the regional impact of the project:

- its seat is in the eligible region;

- the seat of its organizational unit, to which the project relates, is in the eligible region (e.g. the dean’s office, institute management or a branch of the institution), and it has an established infrastructure in the region.

- it is an entity that has a share in eligible project expenses or in projects evaluated as successful in the OP RDI calls 1.1, 1.2 or 2.2 and that declared that it fulfilled the conditions for moving out of Prague (see Article 2.5 of the OP RDI Handbook for Applicants – Priority Axes 1 and 2). The condition is that the eligible expenses of this entity in the project(s) of priority axes 1 and 2 are meant for building infrastructure for the entity in the eligible region(s).

# Form and amount of support

Priority axis 3, support area 3.1 will be fully financed from public funds as follows: 85% from the European Regional Development Fund and 15% from the state budget. The implementation phase of the project will consist of:

- Proof of Concept phase, which will be obligatorily evaluated by the beneficiary at the project level no later than twelve months after the start of the project. A successful individual activity (IA) is an activity for which the technical feasibility and commercial aspects were verified. Activities can also be considered as successful in the case that they have been verified and considered as not suitable for commercialization. Activities that have been evaluated as not suitable for commercialization do not continue to the Preparation for Commercialization phase.

- Preparation for Commercialization phase - the beneficiary shall propose for this phase only those successful individual activities that have passed the Proof of Concept phase with the recommendation to continue. The recommendation to continue is given at the project implementation team level. The beneficiary shall submit its proposal of individual activities to the MA OP RDI for further assessment. MA shall approve which IA will continue to the Preparation of Commercialization phase.

The expenses of the project implementation team for the Preparation of Commercialization phase should be planned with regard to the reduction of individual activities in their financial volume and number. Excluded IAs will be stopped or further funded from other sources outside the OP RDI.

The requirement of the beneficiary to exclude a certain minimum number of individual activities

      - The beneficiary shall first exclude all unsuccessful individual activities of the Proof of Concept phase.

      - After the Proof of Concept phase, the beneficiary will propose the most promising individual activities for the commercialization out of all successful individual activities. These will be recommended for continuation to the Preparation of Commercialization phase. In practice, there may be a situation, where IAs potentially suitable for commercialization can be excluded due to funds reduction. MA grants the decision about list of IAs continuing to the Preparation for Commercialization.

- In its application, the beneficiary shall take into account the resources available for IAs in the Preparation of Commercialization phase. The OP RDI will finance up to so many successful individual activities after the Proof of Concept phase, whose aggregate amount of eligible funds does not exceed 50% of the eligible funding planned for IAs in the Preparation of Commercialization phase.

- The continued IAs will be supported in its originally planned or optimized eligible amount of expenditure except for exceptional cases (for example, one IA continues, whose eligible costs must be potentially reduced as well).

- The applicant prepares the budget assuming 100% subsidy for all IAs in both implementation phases.

The support is provided as a grant. In line with the Framework, the support provided this way to research institutions (direct support) does not constitute public support within the meaning of Article 107 of Treaty on the Functioning of the European Union. Depending on the nature of the project and the legal form of the beneficiary, projects may be funded through regular ex-ante funding or through ex-post funding. The funding method (ex-ante/ex-post) will be specified in the Grant Award Decision and a description is given in the Handbook for Beneficiaries of the OP RDI. The funds awarded will be earmarked to cover eligible project expenditure.

Double financing of an expense from another public resource (national or EU) is inadmissible.

Financial limits

- The minimum eligible expenses of one IA is CZK 1 million, the maximum is CZK 12 million.

- The minimum eligible project costs including its IAs is CZK 3 million, the maximum amount is CZK 50 million.

- The project application shall allocate 20% to 50% of eligible project costs for the Preparation of Commercialization phase.

- The planned volume of funds for the Proof of Concept and Preparation of Commercialization of R&D results phases above individual activities defined in the project application must not be higher than 10% of eligible project costs.

- The total project cost may not exceed CZK 1.1 billion.

Research priorities

The aim of the call is to support larger projects thematically focusing on individual priorities with high commercial potential. The project has its own organizational structure (= project implementation team of technology transfer) linked to the structure of the applicant realizing commercialization-supporting activities. Projects will cover number of individual activities falling within a single national priority of oriented research, experimental development and innovation specified at the RDI objective level as well as within a single priority for applied research, development and innovation (Biological and ecological aspects of sustainable development, Molecular biology and biotechnology, Energy sources, Material research, Competitive engineering, Information society and Security 
and defense).

Grouping IAs under a priority within the project

One applicant must group all IAs belonging to a single main priority for applied research, development and innovation under a single project. This limitation does not apply to partners. Technology transfer of individual activities is provided by the project implementation team of technology transfer. Individual activities will be encapsulated by this general project due to the economical use of resources. There can be a maximum of 10 IAs in the project application. Project application will include a public part (+ summary of individual project activities) and non-public part (a description of individual activities) in order to allow objective evaluation while protecting trade secrets. The Grant Award Decision (Decision) shall only include the public part.

# Implementation period and expense eligibility

Eligible project expenses can occur before the issuance of the Decision. The expenditure made before the Decision was issued must be directly related to the preparatory work on the project; the expenditure is eligible only for projects that have received Decisions and which were created no earlier than 1 January 2012. The nature of the preparatory work will be specified in the Rules of expenditure eligibility for the call 7.3, Area of Support 3.1, Priority Axis 3 ,OP RDI (see Annex B) of this call. Expenses related to the implementation of the project will only be eligible after the issuance of the Decision. The implementation of projects under this call must be completed no later than by 30 October 2015.

In justified cases, the project start date may precede the date of signing the Decision, whereas its justification shall be assessed by the Managing Authority of the OP RDI. In the case the project start date precedes the date the Grant Award Decision was issued, it is possible to incur all eligible expenditure from the project start date without any time restrictions.

# Application for support and its submission

The applicant submits a written application for support to the MA of the OP RDI. An exact specification of the application will be stipulated in the Handbook for applicants.

# Other provisions

No one has a legal title to receiving the grant.

Detailed information necessary to prepare project applications and the conditions for submitting applications not listed here will be available in the Handbook for Applicants available on the website of the OP RDI. The MA OP RDI assumes an external advisor who will monitor the progress of projects.

The Managing Authority of the OP RDI is entitled to prolong, discontinue or cancel the call.

# Address of the announcer and support provider

Ministry of Education, Youth and Sport

CORSO IIa

Křižíkova 34/148

Prague 8 – Karlín

186 00

# Annexes

- Selection criteria for call 7.3 – Support for pre-seed activities

- Rules for expense eligibility for call 7.3 – Support for pre-seed activities

- Monitoring indicators for call 7.3 – Support for pre-seed activities

To exclude doubts, the main objective of the beneficiary shall be any of the activities listed as a) or b), or any combination thereof.

Commercial activities mean offering goods and services on the market (i.e. in R&D particularly contractual research – see Section 3.2.1. of the Framework).

Non-commercial activities in R&D are in particular activities listed in Section 3.1.1. of the Framework.

When evaluating the project, only the relevant unit is considered.

Resolution of the Government of the Czech Republic of 19 July 2012 No. 552 on National Priorities of Oriented Research, Experimental Development and Innovation, see http://www.vyzkum.cz/FrontClanek.aspx?idsekce=653383

National Policy of Research, Development and Innovation of the CR for 2009 – 2015